## Priced schedule
TEST - fictitious. Hartfield Build Ltd - priced Schedule of Works rev A - 14 Larch Walk - tender dated 5 November 2026
Item | Description | Unit | Qty | Rate (GBP) | Amount (GBP)
1 | Site set-up, welfare, scaffold, protection, skip, insurances, construction phase plan | item | 1 | 9800 | 9800
2.1 | Remove existing rear wall incl. window W01 between party wall and new pier | m2 | 11.3 | 85 | 960.5
2.2 | Break out existing patio and dispose | m2 | 28 | 22 | 616
3.1 | Excavate strip foundations 1.0 m deep, cart away | m3 | 9.4 | 95 | 893
3.2 | Concrete strip foundations 600 wide x 225 thick | m | 14.4 | 120 | 1728
3.3 | Ground bearing slab 150 on 100 PIR and DPM | m2 | 21.5 | 78 | 1677
4.1 | Steel beam S1 UB 203x133x25 with padstones, incl. temporary works | item | 1 | 2900 | 2900
5.1 | 300 cavity wall, facing brick to match, full-fill insulation, block inner leaf | m2 | 39 | 245 | 9555
5.2 | Brick parapet with reconstituted stone coping | m | 14.4 | 165 | 2376
6.1 | Flat roof warm deck incl. joists, OSB, 150 PIR, single-ply membrane | m2 | 25.6 | 210 | 5376
6.2 | Rooflights RL1, RL2 1000 x 1500, supply and fix incl. upstands | nr | 2 | 1450 | 3900
7.1 | Aluminium bifold doors D10 4000 x 2100 | nr | 1 | 9200 | 9200
7.2 | Aluminium window W10 1500 x 1200 | nr | 1 | 1350 | 1350
8.1 | Plaster and skim to walls | m2 | 52 | 26 | 1352
8.2 | Plaster and skim to ceiling | m2 | 21.5 | 30 | 645
8.3 | Engineered oak floor, PC sum GBP 45/m2 supply, fix | m2 | 21.5 | 68 | 1462
9.1 | Underfloor heating to the extension, connect to existing boiler | m2 | 21.5 | 95 | 2042.5
9.2 | Electrics: 12 sockets, 8 downlights, 2 pendants, testing and certificate | item | 1 | 2400 | 2400
10.1 | Provisional sum: drain diversion / build-over works | PS |  |  | 3000
10.2 | Provisional sum: fitting client-supplied kitchen | PS |  |  | 2500
11 | Contingency | item |  |  | 5000
| Tender total excluding VAT |  |  |  | 68733
| VAT at 20% |  |  |  | 13746.6
| Total including VAT |  |  |  | 82479.6
Programme: 13 weeks from possession. Tender open for acceptance for 8 weeks.