## Summary
Tender analysis
14 Larch Walk – rear extension, Sevenoaks TN13 · 6 November 2026
| Hartfield Build Ltd | Mereworth Builders Ltd | Oakden Construction Ltd
Tender sum as submitted (excl. VAT) | 68733 | 65330 | 73950
Items recalculated (quantity × rate) | 67733 | 65330 | 73950
Difference (tender sum less recalculated items) | 1000 | 0 | 0
Provisional and prime cost sums levelled to the schedule | 0 | 0 | 1000
Items not priced or excluded (added for comparison) | 0 | 4576.5 | 0
Quantities changed by the tenderer (re-priced) | 0 | 0 | 0
Adjusted for comparison (excl. VAT) | 68733 | 69906.5 | 74950
Registered for VAT | Yes | Yes | Yes
VAT at 20% | 13746.6 | 13981.3 | 14990
Adjusted including VAT | 82479.6 | 83887.8 | 89940
Rank | 1 | 2 | 3
Construction period (weeks) | 13 | 14 | 12
Tender open for acceptance (days) | 56 | 60 | 30
Open for acceptance until | 1 January 2027 | 5 January 2027 | 6 December 2026
As a private client you cannot recover VAT, so the tenders are compared including VAT.
Items a tenderer did not price are added at the median of the other tenderers’ prices, for comparison only.
Note on B5: Tender from Hartfield Build Ltd, dated 5 November 2026, priced schedule, tender total
Note on C5: Tender from Mereworth Builders Ltd, dated 5 November 2026, page 1
Note on D5: Tender from Oakden Construction Ltd, dated 6 November 2026, page 1
Note on C9: 2.1 Remove existing rear wall incl. window W01 between party wall and new pier – £960.50 2.2 Break out existing patio and dispose – £616 4.1 Steel beam S1 UB 203x133x25 with padstones, incl. temporary works – £3,000 “Note: removal of the rear wall and the steel beam are not included - we suggest the client’s structural engineer arranges this separately.” – £0
Note on D9: “Our price excludes the removal and disposal of any asbestos-containing materials.” – not valued “Foundations priced at 1.0 m depth; any extra depth charged at daywork rates.” – not valued 10.1 We have allowed GBP 2,000 for the drainage provisional sum based on our experience. – £0
Note on B12: Tender from Hartfield Build Ltd, dated 5 November 2026
Note on C12: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on D12: Tender from Oakden Construction Ltd, dated 6 November 2026

## Item comparison
Ref | Description | Qty | Unit | Hartfield Build Ltd |  |  | Mereworth Builders Ltd |  |  | Oakden Construction Ltd
|  |  |  | Rate | Amount | Qty × rate | Rate | Amount | Qty × rate | Rate | Amount | Qty × rate
1 | Site set-up, welfare, scaffold, protection, skip, insurances, construction phase plan | 1 | item | 9800 | 9800 | 9800 |  | in section total |  |  | in section total
2.1 | Remove existing rear wall incl. window W01 between party wall and new pier | 11.3 | m² | 85 | 960.5 | 960.5 |  | not priced |  |  | in section total
2.2 | Break out existing patio and dispose | 28 | m² | 22 | 616 | 616 |  | not priced |  |  | in section total
3.1 | Excavate strip foundations 1.0 m deep, cart away | 9.4 | m³ | 95 | 893 | 893 |  | in section total |  |  | in section total
3.2 | Concrete strip foundations 600 wide x 225 thick | 14.4 | m | 120 | 1728 | 1728 |  | in section total |  |  | in section total
3.3 | Ground bearing slab 150 on 100 PIR and DPM | 21.5 | m² | 78 | 1677 | 1677 |  | in section total |  |  | in section total
4.1 | Steel beam S1 UB 203x133x25 with padstones, incl. temporary works | 1 | item | 2900 | 2900 | 2900 |  | not priced |  |  | in section total
5.1 | 300 cavity wall, facing brick to match, full-fill insulation, block inner leaf | 39 | m² | 245 | 9555 | 9555 |  | in section total |  |  | in section total
5.2 | Brick parapet with reconstituted stone coping | 14.4 | m | 165 | 2376 | 2376 |  | in section total |  |  | in section total
6.1 | Flat roof warm deck incl. joists, OSB, 150 PIR, single-ply membrane | 25.6 | m² | 210 | 5376 | 5376 |  | in section total |  |  | in section total
6.2 | Rooflights RL1, RL2 1000 x 1500, supply and fix incl. upstands | 2 | nr | 1450 | 3900 | 2900 |  | in section total |  |  | in section total
7.1 | Aluminium bifold doors D10 4000 x 2100 | 1 | nr | 9200 | 9200 | 9200 |  | in section total |  |  | in section total
7.2 | Aluminium window W10 1500 x 1200 | 1 | nr | 1350 | 1350 | 1350 |  | in section total |  |  | in section total
8.1 | Plaster and skim to walls | 52 | m² | 26 | 1352 | 1352 |  | in section total |  |  | in section total
8.2 | Plaster and skim to ceiling | 21.5 | m² | 30 | 645 | 645 |  | in section total |  |  | in section total
8.3 | Engineered oak floor, PC sum GBP 45/m2 supply, fix | 21.5 | m² | 68 | 1462 | 1462 |  | in section total |  |  | in section total
9.1 | Underfloor heating to the extension, connect to existing boiler | 21.5 | m² | 95 | 2042.5 | 2042.5 |  | in section total |  |  | in section total
9.2 | Electrics: 12 sockets, 8 downlights, 2 pendants, testing and certificate | 1 | item | 2400 | 2400 | 2400 |  | in section total |  |  | in section total
10.1 | Provisional sum: drain diversion / build-over works |  |  |  | 3000 |  |  | in section total |  |  | 2000
10.2 | Provisional sum: fitting client-supplied kitchen |  |  |  | 2500 |  |  | in section total |  |  | 2500
11 | Contingency |  |  |  | 5000 |  |  | in section total |  |  | in section total
The amounts are shown as tendered. The column ‘Qty × rate’ recalculates each priced item; a red cell differs from the amount tendered (see ‘Arithmetical check’).
Note on I3: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L3: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I4: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L4: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I5: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L5: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I6: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L6: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I7: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L7: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I8: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L8: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I9: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L9: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I10: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L10: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I11: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L11: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I12: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L12: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on F13: Quantity × rate gives £2,900.00; the tender shows £3,900.00. Tender from Hartfield Build Ltd, dated 5 November 2026, priced schedule, item 6.2
Note on I13: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L13: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I14: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L14: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I15: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L15: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I16: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L16: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I17: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L17: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I18: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L18: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I19: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L19: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I20: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L20: Tender from Oakden Construction Ltd, dated 6 November 2026
Note on I21: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on I22: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on I23: Tender from Mereworth Builders Ltd, dated 5 November 2026
Note on L23: Tender from Oakden Construction Ltd, dated 6 November 2026

## Arithmetical check
Tenderer | Ref | Description | Qty | Rate | As priced | Correct amount | Difference | Location
Hartfield Build Ltd | 6.2 | Rooflights RL1, RL2 1000 x 1500, supply and fix incl. upstands | 2 | 1450 | 3900 | 2900 | 1000 | Tender from Hartfield Build Ltd, dated 5 November 2026, priced schedule, item 6.2

## Qualifications and gaps
Tenderer | Type | Item or tenderer’s wording | Location | Value for comparison | Basis
Mereworth Builders Ltd | Not priced | 2.1 Remove existing rear wall incl. window W01 between party wall and new pier | Tender from Mereworth Builders Ltd, dated 5 November 2026 | 960.5 | the other tenderer’s price
Mereworth Builders Ltd | Not priced | 2.2 Break out existing patio and dispose | Tender from Mereworth Builders Ltd, dated 5 November 2026 | 616 | the other tenderer’s price
Mereworth Builders Ltd | Not priced | 4.1 Steel beam S1 UB 203x133x25 with padstones, incl. temporary works | Tender from Mereworth Builders Ltd, dated 5 November 2026 | 3000 | median of 2 other prices
Mereworth Builders Ltd | Exclusion | “Note: removal of the rear wall and the steel beam are not included - we suggest the client’s structural engineer arranges this separately.” | Tender from Mereworth Builders Ltd, dated 5 November 2026, page 1 | 0 | Demolition and structure are allowed for separately under missing work in the comparison; no further addition is made here. Patio removal is not expressly addressed and needs confirmation.
Oakden Construction Ltd | Exclusion | “Our price excludes the removal and disposal of any asbestos-containing materials.” | Tender from Oakden Construction Ltd, dated 6 November 2026, page 1 | not valued | outstanding; may change the ranking
Oakden Construction Ltd | Qualification | “Foundations priced at 1.0 m depth; any extra depth charged at daywork rates.” | Tender from Oakden Construction Ltd, dated 6 November 2026, page 1 | not valued | outstanding; may change the ranking
Oakden Construction Ltd | Qualification | “We have allowed GBP 2,000 for the drainage provisional sum based on our experience.” | Tender from Oakden Construction Ltd, dated 6 November 2026, page 1 | 0 | The drainage allowance is increased by £1,000 excluding VAT separately in the comparison to restore the issued £3,000 allowance; no further addition is made for this wording.

## Basis
Basis of this analysis
Before the invitation is sent, the employer decides whether errors in priced documents are dealt with under Alternative 1 or Alternative 2; the choice is stated in the invitation. – JCT Tendering Practice Note 2024, section ‘Examination of Priced Documents and Errors’ (PN/Tender 2024)
Alternative 1: the tenderer is told of the errors and either confirms the tender or withdraws it; the tender sum is not corrected. On confirmation, all rates and prices except preliminaries, contingencies, prime cost sums and provisional sums are adjusted in the same proportion, and both parties initial the adjusted document. – JCT Tendering Practice Note 2024, section ‘The Alternative Provisions’ (PN/Tender 2024)
A tenderer who qualifies a tender is given the chance to withdraw the qualification without changing the price; otherwise the tender may be rejected. – JCT Tendering Practice Note 2024 (PN/Tender 2024)
After examination the lowest (or best) tender free of errors is recommended to the employer for acceptance; all tenderers are told promptly (for a private employer after the award), and the prices of unsuccessful tenderers are not linked to their names. – JCT Tendering Practice Note 2024, section ‘Recommendation, award and notification to tenderers’ (PN/Tender 2024)
Building work to an existing building (extension, alteration, renovation, loft conversion) is normally standard-rated; section 2.1 lists exceptions, among them alterations for a disabled person (0%) and the installation of mobility aids for the elderly in their home (5%). A tenderer who charges another rate is asked which rate applies and why. – HMRC VAT Notice 708, section 2.1 (last updated 26 August 2026)
A business must not show VAT as a separate item on its invoices until it has received its VAT registration number. – HMRC VAT Notice 700/1, section 5.1 (updated 5 August 2026)
A business must register for VAT when its taxable turnover for the last 12 months goes over £90,000 (the VAT threshold); below it, registration is voluntary. – GOV.UK, ‘Register for VAT: when to register’ (undated page)
HMRC’s online service checks whether a UK VAT registration number is valid and to which business name and address it is registered. – GOV.UK, ‘Check a UK VAT number’ (service page, checked 9 October 2026)
3 to 6 tenders are usually enough (design and build at most 4). – JCT Tendering Practice Note 2024, section ‘Number of Tenderers and debriefing’ (PN/Tender 2024)