## Read Me
Field | Basis
Review date | October 13, 2026
Planned filing | November 2026; exact day/channel unknown. November 1 is a lookup anchor only.
Status | Draft; fictitious site. Not filed, accepted or professionally certified.
Baseline | Use the 2025 California Building Standards Code cycle, effective January 1, 2026, with the City's 2026 amendments under Ordinance 188797, effective December 31, 2025. The stated detached, one-story dwelling fits the Los Angeles Residential Code scope; applicable LABC provisions remain incorporated. [S01–S04, S27]
Sources | See Sources tab and linked Word report. Verify effective requirements again before submission.
Assumptions | Ordinary private residential rental; no federal financial assistance or federal lease; confirm owner/operator facts.
Use | Record named responsible person, requested date, city response and closure evidence as confirmed; empty fields are unknown, not zero.

## Permit Matrix
ID | Discipline | Permit / review | Applicability / trigger | Authority | Evidence to collect | Verify / next action | Project evidence | Source ID | Status | Responsible person | Requested date | City response / date | Closure evidence
B01 | building | Filing baseline and amendment record | Required before filing | LADBS | Exact November filing day/channel, accepted application receipt, current ordinance and errata set. | Confirm 2025 state/2026 City baseline, LARC route and incorporated LABC provisions; reconcile online 2022 references in 91.101 and 94.101. Recheck changes immediately before filing. | Documents/Project brief.docx ¦ paragraphs 4–6 ¦ New detached ADU; November 2026 target | S02 | in_review
Z01 | zoning | ADU zoning / ministerial eligibility | Required review; pathway not established | LADBS zoning / Los Angeles City Planning | Real address, APN, legal lot/title, ZIMAS report, existing dwelling permits, boundary/topographic survey and dimensioned site plan. | Confirm applicable Chapter 1 or 1A, current ADU ordinance/state-law pathway, setbacks, height, access, unit count and parking treatment. Check any enacted change after the October 2026 proposal. | Documents/Project brief.docx ¦ paragraphs 3–4 ¦ Fictitious City site; existing single-family house Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No parcel or setback plan supplied | S14 | evidence_needed
Z02 | zoning | Coastal, historic and other overlay approvals | Conditional on real parcel | City Planning / Coastal Commission, if applicable | Coastal boundary, historic designation/HPOZ, specific plan, hillside and other overlay records. | Identify actual planning clearances and any coastal development permit/exemption; resolve state ADU-law limits on local conditions. Do not assume a hearing or discretionary entitlement. | Documents/Project brief.docx ¦ paragraph 3 ¦ Address cannot support parcel search | S13 | evidence_needed
B02 | building | New ADU building permit and plan check | Required | LADBS | Complete site/architectural/structural set, roof plan, elevations, sections, foundation/framing, calculations, door/window placement, egress, smoke/CO and equipment details. | Confirm R-3 / Type V-B, applicable design criteria, professional signatures and submittal checklist. DD floor plan and finish schedule do not establish permit readiness. | Documents/Project brief.docx ¦ paragraph 4 ¦ Supplied occupancy/construction and area Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Only schematic room blocks and notes; no plotted doors/windows | S15 | evidence_needed
B03 | building | Soils, grading, retaining and site structures | Conditional permit/review | LADBS Grading / Geology / Structural | Site grades, cut/fill quantities, foundation criteria, seismic/liquefaction/landslide evidence, retaining/shoring scope. | Determine need for soils/geology reports, grading permit, retaining-wall or shoring permits and haul-route approval. No exemption established. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No site grades or foundation design | S15 | evidence_needed
B04 | building | Electrical permit | Required; separate plan check depends on system | LADBS Electrical | Load calculation, service/meter/panel design, lighting/receptacle layout, grounding, appliance loads and PV connections. | Confirm electrical plan-review threshold, permit packaging and LADWP service requirements under the 2025 California / 2026 LA Electrical Code. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No electrical design supplied | S05 | evidence_needed
B05 | building | Mechanical permit | Required for proposed HVAC/ventilation work | LADBS Mechanical | HVAC sizing/equipment, ventilation/exhaust rates and routing, clearances and condensate details. | Confirm permit and any separate mechanical plan check using 2025 California / 2026 LA Mechanical Code; coordinate energy verification. | Drawings/A-601 Finish Schedule.pdf ¦ p. 1 ¦ Bath and Laundry / Mech. rows ¦ Exhaust fan, water heater and air handler noted without design | S06 | evidence_needed
B06 | building | Plumbing permit | Required | LADBS Plumbing | Fixture schedule, water-heating design, water/drain/waste/vent sizing and connection route. | Ordinance 188797 Sections 520–521 confirm 2025 CPC. Ask LADBS for consolidated City amendments and operative appendices, separate plan-check triggers and existing sewer reuse evidence; hosted 94.101 retains older wording. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Bath/kitchen/laundry labels only | S03 | in_review
B07 | building | Energy review and PV electrical approval | Required energy review; PV subject to documented code exceptions | LADBS / energy designer / LADWP | 2025 CF1R package, verified climate zone, envelope and systems, PV calculation/layout or exception, service rating and required field-verification schedule. | Treat this new detached ADU as new single-family construction. Resolve PV scope, electric readiness and BESS-ready applicability with the 2025 Energy Code. | Documents/Project brief.docx ¦ paragraph 4 ¦ New detached construction Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Energy documents absent | S16 | evidence_needed
B08 | building | CALGreen and City green-building review | Required | LADBS Green Building | Residential checklist; equipment fuel types; roof product/slope; water, materials, waste and site measures. | Apply 2025 CALGreen/2026 LAGBC and local amendments. Design all-electric under 99.04.106.8; attached-ADU gas exception does not match this detached scope. Confirm current enforcement and any claimed exception. | Documents/Project brief.docx ¦ paragraph 4 ¦ Detached ADU Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Fuel types and roof specification absent | S09 | evidence_needed
B09 | building | Demolition / existing-house work | Not indicated in brief; conditional if scope changes | LADBS / relevant clearance agencies | Existing-site survey, removal inventory and explicit scope affecting the primary house. | Confirm no demolition/conversion is proposed; add permits and 2025 CEBC/LA existing-building review if existing work is introduced. | Documents/Project brief.docx ¦ paragraph 4 ¦ New detached unit behind existing house | S29 | in_review
F01 | fire | Operative local fire amendments | Open source conflict — verify before design freeze | LAFD / LADBS | Enacted fire ordinance, effective date and written list of operative amendments for filing. | State baseline is 2025 CFC. Published 57.101 still references 2022 CFC/2021 IFC; Council File 25-1370 records ordinance-preparation action, not an identified final replacement ordinance. Obtain authoritative resolution. | Not supplied | S10 | conflict
F02 | fire | Hydrant/access clearance | Conditional | LAFD Hydrant and Access Unit | Site access distance, roadway/fire-lane geometry, hydrant/water-supply information and current fire-hazard designation. | Handbook flags ADUs more than 150 ft from roadway and detached ADUs in High/Very High Fire Hazard Severity Zones. Obtain referral decision. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No street, hydrant or site-access information | S12 | evidence_needed
F03 | fire | ADU sprinkler determination | Potential statutory exemption; evidence required | LADBS / LAFD | Primary-house permit history and evidence whether sprinklers are legally required, including subsequent alterations. | HCD states ADU sprinklers are not required if the primary residence is not required to have them; ADU construction alone does not trigger primary-house sprinklers. Absence alone is insufficient proof. Obtain written determination; permit system if required. | Documents/Project brief.docx ¦ paragraph 4 ¦ Existing house has no sprinklers; ADU decision unconfirmed | S13 | evidence_needed
F04 | fire | Wildland-urban interface design | Conditional on hazard mapping | LADBS / LAFD | Real parcel, adopted fire-hazard map, site vegetation and proposed exterior assemblies. | Screen 2025 Title 24 Part 7, its emergency supplement and operative City WUI amendments; identify specific assembly and site requirements if triggered. | Documents/Project brief.docx ¦ paragraph 3 ¦ Fictitious address; hazard zone unknown | S24 | evidence_needed
A01 | accessibility | State / local residential access scope | Separate review required | LADBS | Confirmed use/ownership/funding and detailed entrance, bathroom and door layouts. | Confirm applicable California residential access/aging-in-place provisions and any Chapters 11A/11B triggers. Federal screening below does not decide state/local obligations or certify the plan. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Notes give nominal door sizes, not clear openings or maneuvering space | S04 | evidence_needed
A02 | accessibility | ADA Titles II / III | Not indicated for assumed ordinary private residential rental | Owner / operator; federal coverage independent of LADBS | Owner confirmation of long-term residential use, private operation and no public-facing leasing office, lodging, educational or social-service use. | Re-screen if use/operator changes. No ADA permit is identified; private funding alone is not the legal test. | Documents/Project brief.docx ¦ paragraph 5 ¦ Rental after completion; no federal funding | S17 | in_review
A03 | accessibility | FHA design and construction | Not applicable to stated one-unit detached building | Owner / design team; HUD enforcement | Site/building unit-count confirmation and final occupancy/use. | 24 CFR 100.201/100.205 address buildings with at least four dwelling units and qualifying first occupancy. A detached one-unit ADU does not meet that threshold. | Documents/Project brief.docx ¦ paragraph 4 ¦ One ADU behind a separate single-family house | S18 | not_applicable
A04 | accessibility | FHA rental nondiscrimination duties | Potentially applicable; no blanket exemption established | Owner / property manager; HUD | Ownership/entity and portfolio facts, owner occupancy, broker/agent role, advertising and rental policies. | Evaluate exemptions under 100.10 separately from design scope. Where covered, address reasonable accommodations and tenant-funded reasonable modifications; discriminatory advertising restrictions survive listed small-owner exemptions. | Documents/Project brief.docx ¦ paragraphs 3, 5 ¦ Owners unnamed; rental planned | S20 | in_review
A05 | accessibility | Section 504 and ABA funding screen | Not indicated on stated private/no-federal-funds basis | Owner / funding agency, if any | Funding/loan/grant covenants, recipient/subrecipient status, operating subsidies and any federal lease; obtain owner confirmation. | Section 504 depends on covered federal financial assistance, not unit count. HUD 8.3 excludes a landlord from recipient status merely for receiving voucher payments. Re-screen other assistance and any federal lease/ABA trigger. | Documents/Project brief.docx ¦ paragraph 5 ¦ No federal funding Documents/Project brief.docx ¦ paragraph 8 ¦ Federal screening requested | S22 | in_review
FL01 | flood | Floodplain / watercourse clearance | Conditional | BOE floodplain reviewer / LADBS | Parcel-specific current FEMA and City mapping, survey elevations and datum; elevations/design if mapped. | Determine flood clearance, development restrictions and certificates. Floodplain review is separate from zoning and building design. | Documents/Project brief.docx ¦ paragraph 3 ¦ No real parcel or flood evidence | S12 | evidence_needed
S01 | special_agencies | Sewer availability and connection | Sewer clearance required; connection work permit as scoped | BOE / LADBS Plumbing | Existing lateral/location, capacity and connection design; easements. | Obtain sewer availability clearance and confirm public/private connection permits and fees. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ Utility route absent | S12 | evidence_needed
S02 | special_agencies | Water and electrical utility service | Service coordination required; clearance as referred | LADWP | Existing service/meter information, electrical demand, water pressure/demand, easement and overhead-line survey. | Confirm capacity, meter/service configuration, easement clearances, upgrade/interconnection process and timing. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No service design or utility survey | S12 | evidence_needed
S03 | special_agencies | Site drainage and stormwater/LID | Drainage review; LID conditional | BOE / LASAN / LADBS | Drainage plan and total impervious-area change, including paving. | Resolve roof/site drainage clearance. Screen LID using whole-project impervious area, not ADU floor area alone. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No drainage or paving plan | S12 | evidence_needed
S04 | special_agencies | Public right-of-way work | Conditional | BOE / public works bureaus | Utility trench, driveway/curb and sidewalk work limits. | Identify excavation, sewer, A/B or encroachment permits only for actual public-way work. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No public-way work shown | S12 | evidence_needed
S05 | special_agencies | Protected and street trees | Conditional | Urban Forestry / City Planning as applicable | Tree inventory, species, drip lines and construction limits. | Determine protection plan, clearance and any tree-work permit before disturbance. | Drawings/A-101 Floor Plan.pdf ¦ p. 1 ¦ A-101; Rev. 0 - 10/09/2026; DESIGN DEVELOPMENT ¦ No tree/site inventory | S12 | evidence_needed
S06 | special_agencies | School fees and other fee clearances | Verify assessments/exemptions | LADBS / LAUSD / BOE / City Planning | Certified interior livable area, primary dwelling area, exemption basis and fee receipts. | HCD March 2026 guidance exempts ADUs of 750 sf or less of interior livable space from specified impact fees; this does not eliminate school, plan-check, permit or utility charges. Confirm LAUSD assessment. | Documents/Project brief.docx ¦ paragraph 4 ¦ Approx. 720 sf gross is supplied, not certified interior livable area | S13 | evidence_needed
S07 | special_agencies | Inspections / certificate of occupancy | Required closeout | LADBS and referral agencies | Approved plans/permits, inspection records, required testing, energy/green closeout and utility releases. | Confirm final inspection and certificate-of-occupancy sequence before residential use. | Documents/Project brief.docx ¦ paragraph 5 ¦ Rental after completion | S15 | evidence_needed
S08 | special_agencies | Rental registration and housing program review | Required scope determination before renting | Los Angeles Housing Department | Primary-house age/rental status, ADU occupancy certificate, ownership and rental history. | Confirm SCEP, JCO/RSO registration and applicable exemptions. A new detached ADU can affect the existing house's treatment; no operating exemption is assumed. | Documents/Project brief.docx ¦ paragraphs 4–5 ¦ Existing house plus new rental ADU | S23 | evidence_needed

## Code Editions
Discipline | State code | City basis / scope
Residential / Part 2.5 | 2025 California Residential Code (2024 IRC basis) | 2026 LARC; LAMC Ch. IX, Art. 1.5; Ordinance 188797. Appropriate primary route for stated detached one-story dwelling, subject to LADBS confirmation. [S03–S04, S28]
Building / Part 2 | 2025 California Building Code (2024 IBC basis) | 2026 LABC; Ch. IX, Art. 1; applicable provisions incorporated by LARC. Use City administration and adopted amendments. [S02–S04]
Electrical / Part 3 | 2025 California Electrical Code (2023 NEC basis) | 2026 LA Electrical Code; Ch. IX, Art. 3; 93.0101 confirms state edition. [S05, S28]
Mechanical / Part 4 | 2025 California Mechanical Code (2024 UMC basis) | 2026 LA Mechanical Code; Ch. IX, Art. 5; 95.101. [S06, S28]
Plumbing / Part 5 | 2025 California Plumbing Code (2024 UPC basis) | 2026 LA Plumbing Code; Ch. IX, Art. 4. Ordinance 188797 Sections 520–521, printed p. 112, confirm 2025 CPC despite older wording in the hosted code. [S03, S07, S28]
Energy / Part 6 | 2025 California Energy Code | Applies to this new detached ADU as new single-family construction; City energy review. [S01, S16]
Green building / Part 11 | 2025 CALGreen | 2026 LAGBC; Ch. IX, Art. 9, including City residential amendments and all-electric provisions. [S08–S09]
Fire / Part 9 | 2025 California Fire Code (2024 IFC basis) | State baseline applies. Operative City fire amendment package remains unresolved; obtain final ordinance and effective date. [S01, S10–S11, S28]
WUI / Part 7 | 2025 California Wildland-Urban Interface Code | Conditional on site designation; include January 2026 emergency supplement and verify City amendments/cross-references. [S01, S24]
Existing / historic / referenced | 2025 Parts 10, 8 and 12, as applicable | Existing-building provisions if work affects existing structures; historic code only if qualified scope; referenced standards only as adopted. New ADU is not itself an existing-building conversion. [S01, S29]

## Federal Screen
Law | Preliminary result | Basis / sources | Evidence to collect
ADA | Not indicated for the stated ordinary private residential rental. | Private dwellings used solely as residences are outside ordinary Title III facility coverage; Title II concerns state/local government programs. Public-facing rental offices, lodging or other covered uses can change the result. Private financing alone does not establish an exemption. [S17] | Confirm ordinary residential tenancy, private ownership/operation and no covered business, educational or social-service use.
FHA — design / construction | No, for this one-unit detached building as described. | 24 CFR 100.201 covers buildings with four or more units; 100.205 applies to qualifying first occupancy after March 13, 1991. Neither a single ADU nor a separate single-family house meets that building threshold. [S18–S19] | Retain building/unit-count evidence. Re-screen if the project becomes a different housing configuration.
FHA — rental conduct | Potentially yes; do not describe this ADU as wholly FHA-exempt. | Broader rental protections differ from the four-unit design threshold. Small-owner/owner-occupied exemptions have specific conditions; the stated facts do not establish them. Discriminatory advertising restrictions remain under the listed exemptions. Where covered, accommodation policies and permission for reasonable modifications require separate attention. [S20–S21, S30] | Verify ownership form, portfolio, owner occupancy and use of agents/brokers; review leasing and accommodation procedures.
Section 504 | Not indicated if no covered federal financial assistance reaches the owner/operator/program. | Section 504 follows recipient/program funding, including pass-through assistance; a one-unit size is not a general exemption. HUD 24 CFR 8.3 says voucher/housing assistance payments alone do not make a landlord a recipient or subrecipient. [S22] | Confirm grants, subsidies, agreements and recipient status; revisit if federal assistance is introduced.
ABA — supplemental screen | Not indicated; confirm no federal construction funding or lease. | Federal funding/lease and agency jurisdiction control ABA coverage. No such trigger is supplied. [S25] | Obtain owner funding/lease declaration; keep this separate from the Section 504 and ADA screens.

## Sources
ID | Title | URL | Date / edition / limit | Observed
S01 | CBSC — 2025 Title 24 code editions and updates | https://www.dgs.ca.gov/en/BSC/Codes | 2025 edition; effective 2026-01-01; includes January 2026 errata and Part 7 emergency supplement | 2026-10-13
S02 | City Clerk — Council File 25-1217 / Ordinance 188797 | https://cityclerk.lacity.org/lacityclerkconnect/index.cfm?cfnumber=25-1217&fa=ccfi.viewrecord | Adopted 2025-12-12; final ordinance listed 2025-12-24; effective 2025-12-31 | 2026-10-13
S03 | LADBS — Ordinance 188797, 2026 L.A. Amendments to CA Codes | https://dbs.lacity.gov/sites/default/files/efs/forms/pc17/26-ord-188797-260108.pdf | Ordinance effective 2025-12-31; Sec. 2 / printed p. 5 (CBC/CRC), residential scope / printed p. 87, Secs. 520–521 / printed p. 112 (CPC). Official indexed text reviewed; full 44 MB PDF retrieval incomplete. | 2026-10-13
S04 | LAMC 91.5.100 and 91.5.101 — residential scope | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-219830 | 2026 Rev. 9; amendment effective 2025-12-31 | 2026-10-13
S05 | LAMC 93.0101 — electrical edition | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-183649 | Ordinance 188797; effective 2025-12-31 | 2026-10-13
S06 | LAMC 95.101 — mechanical edition | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-187414 | Ordinance 188797; effective 2025-12-31 | 2026-10-13
S07 | LAMC 94.101 — plumbing; online edition discrepancy | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-295029 | 2026 Rev. 9, citing Ordinance 188797, but displayed paragraph retains 2022 edition | 2026-10-13
S08 | LAMC 99.01.101 — Los Angeles Green Building Code | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-214643 | 2026 Rev. 9; 2025 CALGreen adoption; Ordinance 188797 | 2026-10-13
S09 | LAMC 99.04.106 — residential stormwater, cool roof and all-electric measures | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-214849 | All-electric Ordinance 187714 effective 2023-01-23; general application trigger 2023-04-01; current 2026 Rev. 9 | 2026-10-13
S10 | City Clerk — proposed 2026 Fire Code, Council File 25-1370 | https://cityclerk.lacity.org/lacityclerkconnect/index.cfm?cfnumber=25-1370&fa=ccfi.viewrecord | Council action 2026-01-27, final action recorded 2026-01-28; request for ordinance preparation | 2026-10-13
S11 | LAMC 57.101 and 57.101.1 — published fire adoption | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-341790 | 2026 Rev. 9 still references 2022 CFC/2021 IFC; preceding adoption Ordinance 187994 effective 2023-10-04 | 2026-10-13
S12 | LADBS — Building Permit Clearance Handbook | https://dbs.lacity.gov/sites/default/files/efs/pdf/publications/clearance-handbook.pdf | Revision June 11, 2026; see pp. 30–37, 58, 107–114 and relevant agency sections | 2026-10-13
S13 | HCD — Accessory Dwelling Unit Handbook | https://www.hcd.ca.gov/sites/default/files/docs/policy-and-research/adu-handbook-update.pdf | March 2026; pp. 16–18, 20–23, 34–39; statutory updates through January 1, 2026 | 2026-10-13
S14 | Los Angeles City Planning — Housing Policy / ADU sources | https://planning.lacity.gov/plans-policies/initiatives-policies/housing | Undated live index; Ordinance 186481 and ZA Memo 143 listed; older memo must be reconciled to 2026 state law | 2026-10-13
S15 | LADBS — Plan Review & Permitting | https://dbs.lacity.gov/services/plan-review-permitting | Undated live agency process page | 2026-10-13
S16 | California Energy Commission — 2025 Energy Code ADU FAQs | https://www.energy.ca.gov/programs-and-topics/programs/building-energy-efficiency-standards/energy-code-support-center-6/2025 | 2025 Energy Code; effective 2026-01-01; FAQ publication date unstated | 2026-10-13
S17 | U.S. Access Board — Using the ADA Standards, ADA Coverage of Housing | https://www.access-board.gov/ada/guides/chapter-1-using-the-ada-standards/ | Undated guidance; 2010 ADA Standards generally mandatory for covered new construction from 2012-03-15 | 2026-10-13
S18 | 24 CFR 100.201 — covered multifamily dwellings | https://www.ecfr.gov/current/title-24/subtitle-B/chapter-I/part-100/subpart-D/section-100.201 | eCFR displayed currency 2026-10-08 | 2026-10-13
S19 | 24 CFR 100.205 — FHA design and construction | https://www.ecfr.gov/current/title-24/subtitle-B/chapter-I/part-100/subpart-D/section-100.205 | eCFR displayed currency 2026-10-08; first occupancy after 1991-03-13 | 2026-10-13
S20 | 24 CFR 100.10 — FHA exemptions | https://www.ecfr.gov/current/title-24/subtitle-B/chapter-I/part-100/subpart-A/section-100.10 | Current eCFR consulted 2026-10-13; exemption conditions and advertising exception | 2026-10-13
S21 | 24 CFR 100.203 — reasonable modifications | https://www.ecfr.gov/current/title-24/subtitle-B/chapter-I/part-100/subpart-D/section-100.203 | Current eCFR consulted 2026-10-13 | 2026-10-13
S22 | 24 CFR 8.3 — federal assistance and recipient definitions | https://www.ecfr.gov/current/title-24/subtitle-A/part-8/subpart-A/section-8.3 | Current eCFR consulted 2026-10-13; source notes June 2, 1988 and February 27, 1989 | 2026-10-13
S23 | LAHD — Accessory Dwelling Unit | https://housing.lacity.gov/rental-property-owners/accessory-dwelling-unit | Published/last modified September 4, 2025; rental housing and registration guidance | 2026-10-13
S24 | LAMC 91.101 — administration and WUI; online edition discrepancy | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-172187 | 2026 Rev. 9; ordinance effective 2025-12-31; displayed general adoption paragraph retains 2022 | 2026-10-13
S25 | U.S. Access Board — Architectural Barriers Act | https://www.access-board.gov/aba/about.html | Undated agency guidance; registry observed 2026-10-10 | 2026-10-10
S26 | City Planning — Missing Middle LA hearing | https://planning.lacity.gov/missing-middle-la-public-hearing | October 1, 2026 hearing on proposed ordinances; proposal is not adoption evidence | 2026-10-13
S27 | CBSC — Information Bulletin 25-01 | https://www.dgs.ca.gov/-/media/Divisions/BSC/06-News/Information-Bulletins/2025/BSC-Bulletin-25-01-FINAL.pdf | 2025 bulletin; application-received transition at 2026-01-01; registry observed 2026-10-10 | 2026-10-10
S28 | CBSC — 2025 Guide to Title 24, sixth edition | https://www.dgs.ca.gov/-/media/Divisions/BSC/05-Resources/Guidebooks/2025-Guide-toTitle-24---6th-Edition.pdf | 2025 guide, p. 4; model-code lineage | 2026-10-13
S29 | LAMC 91.2.100–101 — existing-building scope | https://codelibrary.amlegal.com/codes/los_angeles/latest/lamc/0-0-0-294531 | Ordinance 188797 effective 2025-12-31 | 2026-10-13
S30 | 24 CFR 100.204 — reasonable accommodations | https://www.govinfo.gov/content/pkg/CFR-2024-title24-vol1/pdf/CFR-2024-title24-vol1-subtitleB.pdf | April 1, 2024 CFR edition; section 100.204; current eCFR direct retrieval unavailable | 2026-10-13

## City Questions
No. | Question | City response / date | Evidence
1 | Confirm the accepted application date/receipt and 2025 state/2026 City code baseline, LARC scope, controlling Ordinance 188797 text and later changes.
2 | Confirm the consolidated building/plumbing text against Ordinance 188797 and provide the operative fire/WUI ordinances, adopted appendices and effective dates.
3 | For the real parcel, confirm ADU pathway, zoning chapter, setbacks/height/access/parking treatment and required planning/coastal/historic clearances.
4 | Confirm whether sprinklers are legally required in the primary dwelling, the ADU exemption determination and any hydrant/access referral.
5 | Issue the parcel-specific clearance list: BOE sewer/drainage/flood/public-way, LADWP, LASAN, Urban Forestry, school fees and other actual referrals.
6 | Confirm state/local accessibility scope, required energy/green documents, all-electric enforcement, trade plan-check packaging and final occupancy steps.