## Register
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes | Raw Fields
RFI | RFI 014 | north entry lintel bearing | answered 09/18 | [5 empty] | Site/Site observation notes 09-29.docx, paragraphs 7-8 | 2026-09-29 |  | Answer date 2026-09-18 is reported in the field report; the response itself is not supplied. Field report paragraph 7 says the north entry lintel is not installed. Answered does not establish construction completion. Due date, responder and closure evidence are not supplied; overdue status cannot be determined. | {"response_date":"2026-09-18","review_as_of":"2026-10-13","overdue_assessment":"Not determinable; reported answered, due date absent","payment_reference":"Pay application/Pay App 04 - Gulf Coast Builders.xlsx, 'Schedule of values'!A5:I5"}
RFI | RFI 015 | roof drain sump depth | open |  |  | 2026-09-22 |  |  | Site/Site observation notes 09-29.docx, paragraph 8 | 2026-09-29 |  | Open since 2026-09-12; response due 2026-09-22 per field report. Seven calendar days past that date on 2026-09-29; 21 days past on 2026-10-13 if still open. No later response supplied. Deadline is recorded as a reported/requested response date; the agreement excerpt does not establish it as contractual. Confirm current status, obtain response, and reconcile with CO 001's 100% payment claim. Responder is not identified; assign follow-up. | {"open_since":"2026-09-12","review_as_of":"2026-10-13","overdue_days_at_field_report":7,"overdue_days_if_still_open":21,"latest_status_evidence_date":"2026-09-29","related_change":"CO 001 (subject association; formal linkage not supplied)","payment_reference":"Pay application/Pay App 04 - Gulf Coast Builders.xlsx, 'Schedule of values'!A11:I11"}
RFI | RFI 016 | shelving blocking height | open |  |  | 2026-10-01 |  |  | Site/Site observation notes 09-29.docx, paragraph 8 | 2026-09-29 |  | Open since 2026-09-24; response due 2026-10-01 per field report. Not overdue on 2026-09-29 (due in two days); 12 calendar days past due on 2026-10-13 if still open. No later response supplied. Deadline is reported/requested, not established as contractual by the agreement excerpt. Obtain response and owner decision on CR 003. RFI response alone does not authorize cost or time. Responder is not identified; assign follow-up. | {"open_since":"2026-09-24","review_as_of":"2026-10-13","overdue_days_at_field_report":0,"overdue_days_if_still_open":12,"latest_status_evidence_date":"2026-09-29","related_change":"CR 003 (subject association; formal linkage not supplied)","payment_reference":"Pay application/Pay App 04 - Gulf Coast Builders.xlsx, 'Schedule of values'!A12:I12"}
change_order | CO 001 | Added roof drains | Signed by owner, contractor, architect 08/14/2026 | owner, contractor, architect |  |  |  |  | Pay application/Change order log.pdf, page 1, CO 001 row; signature date reported in log | 2026-08-14 |  | USD 18,500.00 included in the contract sum on the log's reported all-party signature status. Signed instrument is not supplied. Pay application row 11 claims 100% completion; field report paragraph 8 leaves RFI 015 on roof drain sump depth open. Verify completed change scope through 2026-09-30; signed status does not prove installed completion. No change action due date supplied; overdue status unknown. | {"amount_usd":"18500.00","signed_date_reported":"2026-08-14","signature_evidence":"Change log only; signed instrument absent","review_as_of":"2026-10-13","time_effect":"Not supplied","due_status":"No due date supplied"}
change_order | CO 002 | Delete exterior bench | Signed by owner, contractor, architect 09/02/2026 | owner, contractor, architect |  |  |  |  | Pay application/Change order log.pdf, page 1, CO 002 row; signature date reported in log | 2026-09-02 |  | USD -4,200.00 reduces the contract sum. Signed instrument is not supplied. Omitted from the application SOV and stated contract sum. Obtain revised SOV allocating the credit to the affected base scope and determine whether any deleted bench value was previously or currently billed. Do not deduct the full credit from this payment without tracing earned/billed value. No action due date supplied; overdue status unknown. | {"amount_usd":"-4200.00","signed_date_reported":"2026-09-02","signature_evidence":"Change log only; signed instrument absent","review_as_of":"2026-10-13","time_effect":"Not supplied","due_status":"No due date supplied"}
change_request | CR 003 | Extra shelving blocking | Pending - owner review | owner review |  |  |  |  | Pay application/Change order log.pdf, page 1, CR 003 row; undated log observed 2026-10-13 | 2026-10-13 |  | USD 9,800.00 pending; excluded from approved contract sum and payment under agreement page 1, Art. 5.3. Application row 12 bills it in full. Field report paragraph 8 lists RFI 016 (shelving blocking height), a possible related design question; formal linkage is not supplied. Obtain owner decision and required all-party signed change order before including in payment. No receipt, issue or decision due date supplied; change request cannot be marked overdue. | {"amount_usd":"9800.00","review_as_of":"2026-10-13","time_effect":"Not supplied","due_status":"No due date supplied"}

## RFIs
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes
RFI | RFI 014 | north entry lintel bearing | answered 09/18 | [5 empty] | Site/Site observation notes 09-29.docx, paragraphs 7-8 | 2026-09-29 |  | Answer date 2026-09-18 is reported in the field report; the response itself is not supplied. Field report paragraph 7 says the north entry lintel is not installed. Answered does not establish construction completion. Due date, responder and closure evidence are not supplied; overdue status cannot be determined.
RFI | RFI 015 | roof drain sump depth | open |  |  | 2026-09-22 |  |  | Site/Site observation notes 09-29.docx, paragraph 8 | 2026-09-29 |  | Open since 2026-09-12; response due 2026-09-22 per field report. Seven calendar days past that date on 2026-09-29; 21 days past on 2026-10-13 if still open. No later response supplied. Deadline is recorded as a reported/requested response date; the agreement excerpt does not establish it as contractual. Confirm current status, obtain response, and reconcile with CO 001's 100% payment claim. Responder is not identified; assign follow-up.
RFI | RFI 016 | shelving blocking height | open |  |  | 2026-10-01 |  |  | Site/Site observation notes 09-29.docx, paragraph 8 | 2026-09-29 |  | Open since 2026-09-24; response due 2026-10-01 per field report. Not overdue on 2026-09-29 (due in two days); 12 calendar days past due on 2026-10-13 if still open. No later response supplied. Deadline is reported/requested, not established as contractual by the agreement excerpt. Obtain response and owner decision on CR 003. RFI response alone does not authorize cost or time. Responder is not identified; assign follow-up.

## Submittals
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes

## ASIs
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes

## Change Requests
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes
change_request | CR 003 | Extra shelving blocking | Pending - owner review | owner review |  |  |  |  | Pay application/Change order log.pdf, page 1, CR 003 row; undated log observed 2026-10-13 | 2026-10-13 |  | USD 9,800.00 pending; excluded from approved contract sum and payment under agreement page 1, Art. 5.3. Application row 12 bills it in full. Field report paragraph 8 lists RFI 016 (shelving blocking height), a possible related design question; formal linkage is not supplied. Obtain owner decision and required all-party signed change order before including in payment. No receipt, issue or decision due date supplied; change request cannot be marked overdue.

## Change Orders
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes
change_order | CO 001 | Added roof drains | Signed by owner, contractor, architect 08/14/2026 | owner, contractor, architect |  |  |  |  | Pay application/Change order log.pdf, page 1, CO 001 row; signature date reported in log | 2026-08-14 |  | USD 18,500.00 included in the contract sum on the log's reported all-party signature status. Signed instrument is not supplied. Pay application row 11 claims 100% completion; field report paragraph 8 leaves RFI 015 on roof drain sump depth open. Verify completed change scope through 2026-09-30; signed status does not prove installed completion. No change action due date supplied; overdue status unknown.
change_order | CO 002 | Delete exterior bench | Signed by owner, contractor, architect 09/02/2026 | owner, contractor, architect |  |  |  |  | Pay application/Change order log.pdf, page 1, CO 002 row; signature date reported in log | 2026-09-02 |  | USD -4,200.00 reduces the contract sum. Signed instrument is not supplied. Omitted from the application SOV and stated contract sum. Obtain revised SOV allocating the credit to the affected base scope and determine whether any deleted bench value was previously or currently billed. Do not deduct the full credit from this payment without tracing earned/billed value. No action due date supplied; overdue status unknown.

## Observations
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes

## Punch List
Type | ID | Title | Status | Authority / Reviewer | Received Date | Requested Date | Contractual Due Date | Issued Date | Origin | Origin Date | Origin URL | Notes